## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Start of the week | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13
Sensing and input working package | 2021-11-19: Documentation on the given guides and projects. Chose main languages and technologies Create/adapt project plan Members tasks assignation; 2021-11-26: Preprocessing, noise cancelling, ROIs definition; 2021-12-31: Camera handling; 2022-01-21: Define other necessary sensors, define use-case, preprocessing, noise cancelling.; 2022-05-13: BFMC
Define IMU, distance sensors
Define use-case and test given servers information (localisation on map, cars interaction, gps interaction)
Induce noise on all sensors and systems
Perception and scene understanding working package | 2021-11-26: Lane, intersection detection; 2021-12-31: Traffic signs, lights, pedestrian detection & classification (Object detection)
Position fusion
Define objects properties file
Environmental server interaction
Modify Dashboard
Behaviour and motion plan working package | 2021-11-26: Define project architecture and communication between packages; 2022-01-21: Define decision making --> priorities of actions and state flow
Define path planning and validation
Define robustness and safety measures
Induce noise on systems to valdiate robustness (loss of image, burned image, road search, undefined objects and states)
Vehicle control working packages | 2021-11-26: Lane following and speed control; 2022-02-04: Intersection navigation; 2022-02-25: Simpler action taking maneuvers (parking, stop for traffic sign, stop for traffic light, stop for pedestrian); 2022-03-18: Complex action taking maneuvers (swith lane for static and mobile car, road search)
Final result & Demo | 2021-11-19: Team can control the phisical car remotely; 2021-11-26: Robot can keep a lane, can make a curve; 2022-02-04: Robot can navigate in intersection; 2022-02-25: Robot can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk; 2022-03-18: While detecting and calculating it's position, the robot can dynamicaly go to specified checkpoint, react to traffic lights, interact with other cars and send environemt data)
|  | Team defines and creates it's own physical testing environment |  |  |  | Team defines a way of parallel developing and testing
Deadlines | 2021-12-10: 2021-12-16; 2022-01-14: 2022-01-20; 2022-02-11: 2022-02-17; 2022-03-11: 2022-03-17; 2022-04-15: 2022-04-21; 2022-05-13: 2022-05-19
Checkpoint | 2021-12-10: 1st report; 2022-01-14: 2nd report; 2022-01-28: Lunar New Year; 2022-02-11: 3rd report; 2022-03-11: Mid-term quality gate; 2022-04-15: 4th report; 2022-05-13: Finals
| Ongoing |  |  | Lâm
| Completed |  |  | Trâm
| Future Work |  |  | Khanh
Minh
Khôi